## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | M-1 | 1.Loaded CSV file successfully. 2.Stored and retrieved data in SQlite. 3.Removed noise (URLs,emojis,hashtags,etc). 4.Tokens,Lemmas,POS tags generated. 5.word count,frequency,search,performance comparison. | MUST HAVE |  | Mahi Raj | 3- Completed
2 | 2 | M-2 | 1. sentiment analysis validation,2.topic modeling, 3.Database integration, 4.Report generation,5.Email Notification | MUST HAVE | 1.TextBlob library, 2.scikit-learn, 3.Python multiprocessing, 4.SQLite, 5.smtplib | Mahi Raj | 3- Completed
3 | 3 | M-3 | 1. Implemented LLM-based sentiment analysis on textual data (Tweets and Movies). 2. Performed M2 (TextBlob) vs M3 (LLM) performance comparison. 3. Generated and sent detailed comparison report via email. | MUST HAVE | M-2 | Mahi Raj | 3- Completed
4 | 4 | M-4 | 1.Implement regex-based text cleaning pipeline and preprocessing module. 2.Integrate TextBlob sentiment analysis and store results in SQLite database. 3.Implement RoBERTa-based LLM sentiment analysis and confidence extraction. 4.Build comparison and visualization dashboard using Plotly in Streamlit. 5.Implement automated email reporting with report attachment. 6.Create a user interface for the project using Streamlit with all functional components integrated. | MUST HAVE | M-1,M2,M3,Streamlit | Mahi Raj | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
M-1 | M-1 | 1. Loaded CSV file successfully. 2.Sored and retrived data in SQLite. 3.Removed Noise(URLs,hashtag,emojis). 4.Tokens,Lemmas,POS tags generated. 5.Word count,frequency, ,search, performance comparison. | 2025-09-08 | 2025-09-16 | Mahi Raj | Coding | 3- Completed | 6
M-2 | M-2 | 1. Implement TextBlob-based sentiment analysis for tweets. 2. Apply LDA to discover main topics from tweet text. 3. Use multiprocessing to speed up sentiment and word analysis. 4. Design and connect SQLite database for storing analysis results. 5. Automate report emailing with attachment using SMTP. | 2025-09-18 | 2025-10-03 | Mahi Raj | Coding | 3- Completed | 6
M-3 | M-3 | 1.Research and setup LLM (RoBERTa) environment (PyTorch, Transformers). 2.Implement parallel processing and batch inference for sentiment analysis (m3.py). 3.Develop code for M2 vs M3 comparison, including metrics (Accuracy, F1) and report generation (m2m3.py). 4. Implement email functionality to send the comparison report (m3email.py). 5.Final testing and validation of the entire M-3 pipeline and documentation. | 2025-10-04 | 2025-10-13 | Mahi Raj | Coding | 3- Completed | 10
M-4 | M-4 | 1.Implement regex-based text cleaning pipeline and preprocessing module. 2.Integrate TextBlob sentiment analysis and store results in SQLite database. 3.Implement RoBERTa-based LLM sentiment analysis and confidence extraction. 4.Build comparison and visualization dashboard using Plotly in Streamlit. 5.Implement automated email reporting with report attachment. 6.Create a user interface for the project using Streamlit with all functional components integrated. | 2025-10-15 | 2025-10-28 | Mahi Raj | Design | 3- Completed | 10

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-09-09 | Multiprocessing | Done
1 | 2025-09-10 | choosen SQLite as database | implemented successfully
1 | 2025-09-15 | choosen a dataset | tweets database choosen
1 | 2025-09-16 | milestone 1 presentation | presented and found no mistake
2 | 2025-09-18 | None | setup environment and verified dependency
2 | 2025-09-23 | LDA model slow convergence | Reduced number of topics and iterations
2 | 2025-09-26 | Email authentication issue | Generated new gmail app password
2 | 2025-10-01 | None | Final validation and report testing completed
3 | 2025-10-04 | Initial setup of the HuggingFace environment and PyTorch dependencies. | Resolved by setting up a dedicated Python virtual environment.
3 | 2025-10-09 | Batch size tuning and parallel processing to fit within the 12-hour window on available hardware. | Implemented parallel batch processing with a batch size of 16 and fixed MAX_LENGTH to 128 as per m3.py configuration.
3 | 2025-10-10 | Integrating M2 database extraction with M3 CSV to ensure sample consistency for fair comparison. | Used a merge/join operation based on a unique identifier (implied in m2m3.py) to align the datasets before comparison.
3 | 2025-10-13 | Final review of the email attachment code, ensuring the app password is secure and not hardcoded (for production) | Successfully tested the email sending functionality using a Gmail App Password, ensuring files are attached correctly.
4 | 2025-10-15 | Over-aggressive regex removed important tokens and emojis. | Adjusted regex patterns to preserve sentiment words and retested with varied datasets.
4 | 2025-10-15 | Encoding mismatch (UTF-8 vs Latin-1) while reading CSVs. | Added encoding handling and fallback logic; verified inserts through row-count check.
4 | 2025-10-17 | Model download and GPU memory limitations. | Cached pretrained model locally and switched to CPU fallback when GPU unavailable.
4 | 2025-10-23 | Plotly visualizations lagged on large data samples. | Implemented data sampling and layout caching to improve render performance
4 | 2025-10-27 | SMTP connection failed due to missing app-password. | Configured secure app password and verified delivery with multiple test addresses.
4 | 2025-10-28 | Resolved all the issues. | Successfully presented the login page and dashboard to the mentor.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-08 | 2025-09-16 | Mahi Raj | selecting and loading textual datasets(CSV),validating their structure and sampling rows. | Parallel processing and result storage | No | No
2 | 2 | 2025-09-18 | 2025-10-03 | Mahi Raj | Automating reports and testing regularly. | Manual result varification | Structured modular coding | No
3 | 3 | 2025-10-04 | 2025-10-14 | Mahi Raj | Documenting the specific RoBERTa model configuration and hyperparameters used for sentiment analysis in the final report. | Spending excessive time on data cleaning for M3, as the processed M2 data was already clean; focus should be on model performance. | Utilizing Parallel processing/batching for performance-intensive tasks,and providing detailed quantitative comparison of different approaches(M2 vs M3). | No
4 | 4 | 2025-10-15 | 2025-10-28 | Mahi Raj | Started with the designing of the UI using streamlit, also added a login/registration page. | completed with the testing and presentation part | started working for the ppt | No
5
6
7